## TIMELINE
[7 empty] | REVISION | COLOR | QTY RANGE
[7 empty] | A |  | 10 | 20
[7 empty] | B |  | 300 | 10000
[7 empty] | C |  | 5000 | 100000
[7 empty] | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE
GOAL | TIME | $FEE | $TOOL | $UNIT | NUM | $EXT | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Minor PCB changes | 5 | [5 empty] | JANUARY 1: 5
Moldable case design for A | 6 | [5 empty] | JANUARY 1: 6
Build and populate batch of REV A PCBs | 5 |  | 300 | 50 | 120 | 6000 | JANUARY 1: 5; JANUARY 2: 0; JANUARY 3: 0
Fabricate REV A cases - print vs. urethane casting | 5 |  | 1000 | 20 | 120 | 2400 | JANUARY 2: 5; JANUARY 3: 0
A COSTS | 21 | 1575 | 1300 |  |  | 8400
REV B planning & estimation - optimization/supply chain/features/power | 35 | [5 empty] | JANUARY 2: 7; JANUARY 3: 7; JANUARY 4: 7; FEBRUARY 1: 7; FEBRUARY 2: 7
Industrial Design - case/materials/cables/connectors/interfaces/fabric | 18 | [5 empty] | JANUARY 2: 3; JANUARY 3: 3; JANUARY 4: 3; FEBRUARY 1: 3; FEBRUARY 2: 3; FEBRUARY 3: 3
PCB B Layout | 32 | [5 empty] | FEBRUARY 1: 8; FEBRUARY 2: 8; FEBRUARY 3: 8; FEBRUARY 4: 8
Case B Engineeirng | 28 | [5 empty] | FEBRUARY 1: 7; FEBRUARY 2: 7; FEBRUARY 3: 7; FEBRUARY 4: 7
Source & Order PCB Components | 8 |  |  | 35.464 | 2000 | 70928 | FEBRUARY 3: 4; FEBRUARY 4: 2; MARCH 1: 2
Case B Proto/Test | 1 |  |  | 100 | 1 | 100 | FEBRUARY 4: 1; MARCH 1: 0
PCB B Proto/Test | 3 |  | 300 | 50 | 1 | 50 | FEBRUARY 4: 3; MARCH 1: 0; MARCH 2: 0
Case B Production Run | 5 |  | 12000 | 7 | 2000 | 14000 | MARCH 2: 3; MARCH 3: 2; MARCH 4: 0
PCB B Production Run | 26 |  | 300 | 15 | 2000 | 30000 | MARCH 2: 14; MARCH 3: 5; MARCH 4: 5; APRIL 1: 2
Cables Production Run | 0 |  | 200 | 2 | 2000 | 4000 | MARCH 2: 0; MARCH 3: 0; MARCH 4: 0
Straps Production Run | 0 |  | 200 | 2 | 2000 | 4000 | MARCH 2: 0; MARCH 3: 0; MARCH 4: 0
REV B final assembly & test | 10 | [5 empty] | APRIL 1: 5; APRIL 2: 5; APRIL 3: 0; APRIL 4: 0; MAY 1: 0
Shipping REV B | 0 | [5 empty] | APRIL 3: 0; APRIL 4: 0; MAY 1: 0; MAY 2: 0; MAY 3: 0; MAY 4: 0
B COSTS | 166 | 12450 | 13000 |  |  | 123078
Sourcing high volume manufacturers & partners | 0 | bar: FEBRUARY 3 to JUNE 4
Industrial Design Push REV C | 0 | bar: MARCH 2 to JUNE 4
Engineering changes for REV C | 0 | bar: APRIL 1 to JUNE 4
C COSTS | 0 | 0 | 0 |  |  | 0
TOTALS | 187 | 14025 | 14300 |  |  | 131478 | 16 | 15 | 10 | 10 | 25 | 25 | 22 | 21 | 2 | 17 | 7 | 5 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FULL PRODUCTION COST (2000 units) |  | 159803

## CHANGES
REV A | 11275
power rewiring
larger on/off switch
remove JTAG
bluetooth enable
change resistor values
cutouts for display/connectors
FC-145 replacement
REV B | 148528
Aesthetic refinement
Battery
Instrument Connector
Display
Encoder
Smaller MCU
EEPROM
PCB/Case Fit
Mounting/Carrying options
Panelize Board
Component sourcing verify
Optimize case for high vol prod

## FEE & COST SCHEDULE
TOOLING COSTS
| URETHANE MOLDS/SETUP | 500
| INJECTION MOLDS/SETUP | 6000
| INJECTION SETUP ONLY | 300
| PCB STENCILS/SETUP | 300
| CABLES SETUP | 200
| FABRIC SETUP | 200
ENGINERING
| HOURLY | 75

## BOM
LEVEL 1 | LEVEL 2 | 1K |  | 10K
CIRCUIT BOARD |  | 50.464 |  | 15.5
| E-BOM |  | 35.464 |  | 12
| PRINTED PCB |  | 3 |  | 0.5
| PCB ASSY |  | 12 |  | 3
CASE SIDE A |  | 3.5 |  | 1.25
CASE SIDE B |  | 3.5 |  | 1.25
INSTRUMENT STRAPS |  | 7 |  | 0.8
| FABRIC |  | 3 |  | 0.3
| CABLE |  | 4 |  | 0.5
TOTAL |  | 64.464 |  | 18.8
TOTAL EXT |  | 64464 |  | 188000

## E-BOM
REFERENCE DESCRIPTOR | DESCRIPTION | SPEC | MFG | MFG # | PATTERN | PATTERN TYPE | COMP TYPE | REEL QTY | QTY | $1K | $10K | $100K | $1K EXT | $10K EXT | $100K EXT | VENDOR | VEND # | 1K LEAD WKS
U4 | Bluetooth Low Energy Radio | BLE112 | Bluegiga | BLE112 | BLE112 | LEADLESS | IC |  | 1 | 10.15 |  |  | 10.15 |  |  | DIGIKEY | 1446-1017-1-ND
U2 | ARM Microcontroller | ATSAM3X8EA-AU | Atmel | ATSAM3X8EA-AU | LQFP144 | SMD | IC |  | 1 | 6 |  |  | 6 | 0 |  | DIGIKEY | ATSAM3X8EA-AU-ND
B1 | Battery | 860mAh |  | 063048 860mAh | Battery |  |  |  | 1 | 6 |  |  | 6
U3 | MIDI Chip | VS1053 | VLSI | VS1053 | LQFP-48 |  |  |  | 1 | 3.42 |  |  | 3.42
Y1 | CRYSTAL-3.2-2.5 | 12MHz KX-7 20pF | KX-7T REPLACEMENT | ECS-120-20-33-CKM-TR | KX-7T REPLACEMENT |  | CRYS |  | 1 | 1.75 |  |  | 1.75 |  |  | DIGIKEY | XC1810CT-ND
D2 | 7 Segment LED Display | LDD-F304NI-RA | Lumex Opto/Components Inc. |  | LDD-E304NI-RA |  | UI |  | 1 | 1.52 |  |  | 1.52
B1 | Slider Switch SPDT |  | TE Connectivity | MLL1200S | MLL1200S |  |  |  | 1 | 1.23 |  |  | 1.23 |  |  | DIGIKEY | 1276-6331-1-ND
Y2 | RESONATOR_EPSON_FC_145 | 32.768Khz | Epson | FC-145 32.7680KD-AC3 | RESONATOR_EPSON_FC_145 |  | CRYS |  | 1 | 0.99 |  |  | 0.99 |  |  | DIGIKEY | SE2413CT-ND
U5 | 3.3 Volt LDO Regulator |  | STMicroelectronics | LD39080DT33-R | TO252-3(4)/10x6.6x2.28 |  |  |  | 1 | 0.78 |  |  | 0.78 |  |  | DIGIKEY | 568-10198-1-ND
U8 | Rotary Pushbutton Encoder | PEC16-2115F-S0012 | Bournes | PEC16-2115F-S0012 | PEC16-2115F-S0012 |  | UI |  | 1 | 0.677 |  |  | 0.677 |  |  | DIGIKEY | PEC16-2115F-S0012-ND
J1 | 1/8" Headphone Jack | 35RASMT2BHNTRX | Switchcraft Inc | 35RASMT2BHNTRX | 35RASMT2BHNTRX |  |  |  | 1 | 0.61 |  |  | 0.61 |  |  | DIGIKEY | 475-1410-1-ND
Y3 | CRYSTAL5X3 | 12.288MHz | SPK | SPK-12M288-5032 | CRYSTAL-SMD-5X3 |  |  |  | 1 | 0.5 |  |  | 0.5 |  |  | DIGIKEY | 568-10019-1-ND
U6 | MCP73831 | MCP73831 | Microchip Technology | MCP73831T-2DCI/OT | SOT23-5 |  |  |  | 1 | 0.42 |  |  | 0.42 |  |  | DIGIKEY | 67-1516-5-ND
X1 | USB Micro B Connector | Micro USB | FCI | 10118194-0001LF | USB-MICROB |  | CON |  | 1 | 0.25 |  |  | 0.25 |  |  | DIGIKEY | 609-4618-1-ND
H1 | Instrument In |  | On Shore Inc. | 302-S241 | 12x2 |  | CON |  | 1 | 0.25 |  |  | 0.25
Z1, Z2 | VARISTORCN0603 | CG0603MLC-05E | Bournes | CG0603MLC-05E | CT/CN0603 |  | STD |  | 2 | 0.103 |  |  | 0.206 |  |  | DIGIKEY | CG0603MLC-05ECT-ND
Q1 | PBSS4130PAN |  | NXP | PBSS4130PAN,115 | SOT1118 |  |  |  | 1 | 0.202 |  |  | 0.202
U7 | ULN2003D |  | STMicroelectronics | ULN2003D1013TR | SOIC-16/150mil |  |  |  | 1 | 0.187 |  |  | 0.187 |  |  | DIGIKEY | ED10525-ND
U1 | LD6806F/18P,115 |  | NXP | LD6806F/18P,115 | SOT886 |  |  |  | 1 | 0.185 |  |  | 0.185 |  |  | DIGIKEY | MCP73831T-2DCI/OTCT-ND
L1, L2, L3, L4 | WE-CBF_0805 | MH2029-300Y | Bournes | MH2029-300Y | 805 |  |  |  | 4 | 0.02 |  |  | 0.08 |  |  | DIGIKEY | MH2029-300YCT-ND
D1 | LED0603 | RED | Osram Opto | LG R971-KN-1 | LED-0603 |  |  |  | 1 | 0.043 |  |  | 0.043
L5 | IND_0804 | FB 1kOhm | Samsung ElectroMechanics | CIM21J102NE | IND_0804 |  |  |  | 1 | 0.014 |  |  | 0.014
C1, C9, C11, C12, C34 | CPOL-EUSMCB | 10u |  |  | SMC_B | SMD | STD |  | 5 |  |  |  | 0 |  |  | DIGIKEY | 497-2345-1-ND
C2, C3, C4, C5, C6, C7, C8, C10, C13, C14, C15, C16, C17, C18, C23, C24, C33 | C-EUC0402 | 100n |  |  | C0402 | SMD | STD |  | 17 |  |  |  | 0 |  |  | DIGIKEY | SC1489-1-ND
C19, C20, C21, C22, C27, C28, C29, C30, C31, C32 | CAP0402-CAP | 100nF |  |  | 0402-CAP | SMD | STD |  | 10 |  |  |  | 0 |  |  | DIGIKEY | 450-1577-ND
C25, C26 | CAP0402-CAP | 1uF |  |  | 0402-CAP | SMD | STD |  | 2 |  |  |  | 0
C35, C38, C40, C44, C47, C48, C52, C53 | CAP0402-CAP | 10pf |  |  | 0402-CAP | SMD | STD |  | 8 |  |  |  | 0
C36, C37, C45 | C-EUC0402 | 22p |  |  | C0402 | SMD | STD |  | 3 |  |  |  | 0
C39, C42 | C-EUC0402 | 22pF_NM |  |  | C0402 | SMD | STD |  | 2 |  |  |  | 0
C41, C46 | CAP0402-CAP | 18pF |  |  | 0402-CAP | SMD | STD |  | 2 |  |  |  | 0
C43 | CAP0402-CAP | 0.1uF |  |  | 0402-CAP | SMD | STD |  | 1 |  |  |  | 0
C49 | CAP0402-CAP | 47nF |  |  | 0402-CAP | SMD | STD |  | 1 |  |  |  | 0
C50, C51 | CAP0402-CAP | 10nF |  |  | 0402-CAP | SMD | STD |  | 2 |  |  |  | 0
C54, C55, C56, C57 | CAP_0603 | 1 uF |  |  | CAP_0603 | SMD | STD |  | 4 |  |  |  | 0
C58 | CAP_0603 | 2.2uF |  |  | CAP_0603 | SMD | STD |  | 1 |  |  |  | 0
C59 | C-EUC0402 | 10n |  |  | C0402 | SMD | STD |  | 1 |  |  |  | 0
C60, C61 | CAP0402-CAP | 4.7uF |  |  | 0402-CAP | SMD | STD |  | 2 |  |  |  | 0
R1 | R-EU_R0402 | 100K |  |  | R0402 | SMD | STD |  | 1 |  |  |  | 0
R2, R3, R6, R7, R10, R12, R13, R15, R19, R22, R23, R24, R25 | RESISTOR0402-RES | 1M |  |  | 0402-RES | SMD | STD |  | 13 |  |  |  | 0
R4 | R-EU_R0402 | 0R_NM |  |  | R0402 | SMD | STD |  | 1 |  |  |  | 0
R5, R8, R20, R21, R38 | RESISTOR0402-RES | 100k |  |  | 0402-RES | SMD | STD |  | 5 |  |  |  | 0
R9, R11 | R-EU_R0402 | 39R 1% |  |  | R0402 | SMD | STD |  | 2 |  |  |  | 0
R14 | R-EU_R0603 | 6k8 1% |  |  | R0603-ROUND | SMD | STD |  | 1 |  |  |  | 0
R16 | RESISTOR0402-RES | 10 |  |  | 0402-RES | SMD | STD |  | 1 |  |  |  | 0
R17, R18 | RESISTOR0402-RES | 20 |  |  | 0402-RES | SMD | STD |  | 2 |  |  |  | 0
R26 | R-EU_R0402 | 0R |  |  | R0402 | SMD | STD |  | 1 |  |  |  | 0
R27 | RESISTOR0402-RES | 2K |  |  | 0402-RES | SMD | STD |  | 1 |  |  |  | 0
R28 | RESISTOR0402-RES | 330 |  |  | 0402-RES | SMD | STD |  | 1 |  |  |  | 0
R29, R33 | RESISTOR0402-RES | 380 |  |  | 0402-RES | SMD | STD |  | 2 |  |  |  | 0
R30, R31 | RESISTOR0402-RES | 4.7K |  |  | 0402-RES | SMD | STD |  | 2 |  |  |  | 0
R32 | RESISTOR0402-RES | 4.7k |  |  | 0402-RES | SMD | STD |  | 1 |  |  |  | 0
R34, R35, R36, R37 | RESISTOR0402-RES | 2k2 |  |  | 0402-RES | SMD | STD |  | 4 |  |  |  | 0